## Dashboard
Determining the Compatibility of the Network Functions of the 5G Core Implementations Open Air Interface and Open5GS
Timeline |  | Phase | Work Type | Tasks Status | Completed
Start Date | End Date |  |  |  | In- Progress
14.08.2023 | 25.08.2023 | 1 | Literature review and learning the theoretical background |  | Pending
26.08.2023 | 31.08.2023 | 2 | Analysis of the requirements
01.09.2023 | 06.09.2023 |  | Submission of Requirement analysis
07.09.2023 | 12.09.2023 |  | Update document based on feedback
13.09.2023 | 22.09.2023 | 3 | Drafting use cases
23.09.2023 | 2.10.2023 | 4 | Test environment setup, PC configuration
03.10.2023 | 15.10.2023 |  | Test environment setuo using Docker
16.10.2023 | 30.11.2023 | 5 | Implementation of use cases
01.12.2023 |  | 6 | Request for feedback from supervisor
25.12.2023 |  |  | Sumission of project draft
01.01.2024 | 15.01.2024 |  | Update project document and upload it in git
30.01.2024 |  | 7 | Final submission of project in examination office