## Dashboard
Determining the Compatibility of the Network Functions of the 5G Core Implementations Open Air Interface and Open5GS
Week | Timeline
1 | 14/08/23 -20/08/23
2 | 21/08/23 -27/08/23 | Phase 1 | Requirement Analysis |  |  | Start date | End date | Tasks
3 | 28/08/23 -03/09/23 |  |  |  |  | 2023-08-14 | 2023-09-03
4 | 04/09/23 -10/09/23 |  |  |  |  | (week 1) | (week 3)
5 | 11/09/23 -17/09/23
6 | 18/09/23 -24/09/23
7 | 25/09/23 -01/10/23 | Phase 2 | Test Environment Setup |  |  | 2023-09-04 | 2023-10-01
8 | 02/10/23 -08/10/23 |  |  |  |  | (week 4) | (week 7)
9 | 09/10/23 -15/10/23
10 | 16/10/23 -22/10/23
11 | 23/10/23 -29/10/23 | Phase 3 | Test Case design |  |  | 2023-10-02 | 2023-10-29
12 | 30/10/23 -05/11/23 |  |  |  |  | (week 8) | (week 11)
13 | 06/11/23 -12/11/23
14 | 13/11/23 -19/11/23
15 | 20/11/23 -26/11/23 | Phase 4 | Test Execution |  |  | 2023-10-30 | 2023-12-03
16 | 27/11/23 -03/12/23 |  |  |  |  | (week 12) | (week 17)
17 | 04/12/23 -10/12/23
18 | 11/12/23 -17/12/23
19 | 18/12/23 -24/12/23 | Phase 5 | Documentation & Presentation |  |  | 2023-12-11 | 2024-01-15
20 | 25/12/23 -31/12/23 |  |  |  |  | (week 18) | (week 22)
21 | 01/01/24 -07/01/24
22 | 08/01/24 -15/01/24 |  |  | To do | In Progress | Completed

## Requirement Analysis
Requirement Analysis
Tasks | To Do
In Progress
Completed
Roadblocks:

## Test setup
Test Environment Setup
Tasks | To Do
In Progress
Completed
Roadblocks:

## Test case design
Test Case Design
Tasks | To Do
In Progress
Completed
Roadblocks:

## Test execution
Test Execution
Tasks | To Do
In Progress
Completed
Roadblocks:

## Documentation & Presentation
Documentation & Presentation
Tasks | To Do
In Progress
Completed
Roadblocks: